## Slide 1: PDTP-DLP 2016 JKUAT POSTIVO BGH QUARTERLY REPORT
Presented by: Brenda Mona.
Stanslaus W. Mwongela
Nazra Mohammed

## Slide 2: Introduction
​
The first assignment for pdtps was the Digital Literacy program this is our report;
This report highlights:
    Achievements
    Milestones
    Experiences
    Challenges
    Recommendations

## Slide 3: Digital literacy program milestones
Lorem ipsum lorem ipsum lorem ipsum lorem ipsum

## Slide 4: Milestones
This section presents a National Summary of all the counties that were under JKUAT UNIVERSITY – JP SA COUTO:
  A total of 7078 schools were inspected in the counties and MOI and JP SA COUTO
  Of the schools inspected 3699 were ready for installation of DLP devices
  Through that process 751 schools in 15 counties received devices.

## Slide 5: Objectives of DLP
Provision of content for digital learning
Provision of digital devices for both learners and teachers
Capacity development for teacher and implementers
Establishment of local assembly for digital devices and related
accessories
Broadband connectivity

## Slide 6
.
ACHIEVEMENTS-MOI
Number of schools
Schools inspected
Schools Ready
installed
Number Of Schools
12807


Number of Schools Inspected
11130

Schools Ready
6640

Schools Installed
1631

## Slide 7: Achievements
Training was done for teachers by JKUAT Co-curriculum support officers.
Active local assembly in various locations e.g Mombasa and Eldoret.
Facilitation of schools in terms of infrastructure e.g power supply, Financing of ICT rooms.
Sensitization of the programe through DLP launches.

## Slide 8: Challenges
Urban
Teacher training was done too early some as early 2012 due to lack of practice some teachers forgot what they learnt.
Access to slum areas in terms of insecurity intraversing
Semi urban
Database :
  Headteachers contacts not up to date
  Double registrations of schools
Rural
Language barrier with locals made it difficult for quality inspectors to traverse some areas in the county
Resources; The ratio of distribution of quality inspectors to different counties.
Terrain, transportation and security.

## Slide 9: Lessons learnt
Training
TOT understood components in Net support
Training of teachers should run concurrent with installation of devices
Tusome syllabus should be integrated into Net support
Training for physically challenged was not addressed eg curriculum(net support)
E-readiness
Route mapping of schools should involve the locals
Communication on standard ICT room should have been made prior
Installation eg storage room, desks
Extra devices for back-up during installation.

## Slide 10: Recommendation
More resources should be allocated to the primary schools so that they can upgrade their facilities
There should be technical support team in case of any problem that arises within the county
The delivery and installation of the devices should be done as soon as the teachers are trained so as to give them an opportunity to immediately apply the skills learnt
Periodical training of teachers in modules
Need to ensure sufficient voltage to schools with low voltage

## Slide 11
The Early Childhood Development (E.C.D) colleges need to implement and incorporate ICT curriculum to their program especially the DLP Training

## Slide 12: THANKS!