
**REPULIC OF KENYA**



**MINISTRY OF LAND & PHYSICAL PLANNING**

**PROGRESS REPORT AS AT 31ST AUGUST 2017 BY OSCAR RAHA**

1. **Digitization**
   1. Green Cards

* All green cards have been scanned and up to date.
* Data Entry for New Cards is completed and up to date
* Now doing data entry for Added Entries and will be up to date in the next 2 weeks.
  1. White Cards

All white cards are scanned and updated.

* 1. Parcel Files
* Have started scanning for Parcel Files.

1. **Computers**

From the 15 requested we have received 5 pieces and awaiting security clearance before they are installed.

1. **Security**

In July there was a break in at the registry where some computers were stolen. It is highly recommended we have security guards in the registry to ensure that the progress of digitization is not stalled due to lack of equipment.

1. **Networking and Support**

Contractors completed the network infrastructure but didn’t manage survey Office Switch isn’t working and might need a new Switch. Support is being offered whenever needed.